DOCGEN

Local Document Creator & Editor

2-Week Build Plan  |  Execution Roadmap  |  Day-by-Day Task Board  |  Claude Pro Guide

| 14 Days Build Timeline | 2 Devs Team Size | Claude Pro AI Assistant |
| --- | --- | --- |

Table of Contents

1.  Project Overview & Goals

2.  Recommended Tech Stack

3.  Detailed Project File Structure

4.  2-Week Phased Roadmap

5.  Day-by-Day Task Board (Jira / MS Planner)

6.  Claude Pro Usage Guide

7.  Master Prompt for Claude Code Execution

8.  Risks & Mitigations

1. Project Overview & Goals

DocGen is a fully self-hosted, locally-deployed document creation and transformation application. It has two core modules: a Document Creator that generates professional Purchase Orders (POs) and Memorandums of Understanding (MOUs) from structured form input, and a Document Editor/Transformer that reads an uploaded PO or MOU and regenerates it in a different company's format using local AI. The entire stack — including AI inference — runs locally with zero external API calls.

Core Modules

Module A: Document Creator

User selects document type (PO or MOU) and target company template

Frontend renders a dynamic form from the template's JSON schema

User fills in: vendor, buyer, dates, line items, amounts, payment terms

FastAPI backend validates input, renders Jinja2 template, generates PDF or DOCX

Output file is saved locally and returned for download

Module B: Document Editor / Transformer

User uploads an existing PO or MOU (PDF or DOCX)

Backend parses the file using pdfplumber / python-docx

Local LLM (via Ollama) extracts all structured fields into JSON

User reviews and corrects the extracted fields in an editable form

User selects a target company template — the doc is regenerated in the new format

Non-Negotiable Constraints

- 100% local — no external API calls, no cloud dependencies

- Deployable — Docker Compose single-command setup for intranet offices

- Professional document output — PDF (WeasyPrint) and DOCX (docxtpl)

- AI must run locally — Ollama with Mistral 7B or LLaMA 3.1 8B

2. Recommended Tech Stack

| Layer | Technology | Details / Justification |
| --- | --- | --- |
| Frontend | React 18 + Vite | TypeScript, TailwindCSS, React Hook Form, Axios |
| Backend API | FastAPI (Python 3.11) | uvicorn, pydantic v2, python-multipart, aiofiles |
| Local AI Runtime | Ollama (primary) | Mistral 7B Instruct Q4_K_M / LLaMA 3.1 8B fallback |
| Doc Generation | Jinja2 + WeasyPrint | python-docx, docxtpl for DOCX; WeasyPrint for PDF |
| Doc Parsing | pdfplumber + python-docx | pytesseract (OCR fallback), Pillow |
| Database | SQLite (MVP) | SQLAlchemy ORM, Alembic for migrations |
| File Storage | Local filesystem | /data/uploads, /data/outputs — mountable volume |
| Containerization | Docker Compose | 3 services: nginx, fastapi-uvicorn, ollama |
| State Management | Zustand (React) | Lightweight, no boilerplate, persists to localStorage |
| HTTP Client | Axios + React Query | Caching, retry logic, loading states out of the box |

Model Strategy

Primary: Mistral 7B Instruct Q4_K_M (via Ollama)

Best speed/accuracy tradeoff for structured JSON extraction

Runs on 8GB RAM CPU machines — accessible to most office hardware

Use: ollama pull mistral:7b-instruct-q4_K_M

Fallback: LLaMA 3.1 8B Instruct Q4_K_M

Higher extraction accuracy for complex multi-page POs

Requires 12GB RAM or GPU with VRAM

Use: ollama pull llama3.1:8b-instruct-q4_K_M

Low-resource option: Phi-3 Mini 3.8B

For machines with only 4–6GB RAM

Adequate for simple field extraction; struggles with complex tables

Use: ollama pull phi3:mini

3. Detailed Project File Structure

docgen/ ├── docker-compose.yml ├── .env.example ├── README.md │ ├── frontend/ # React + Vite + TypeScript │ ├── Dockerfile │ ├── nginx.conf │ ├── src/ │ │ ├── components/ │ │ │ ├── DocumentCreator/ │ │ │ │ ├── CreatorForm.tsx # Main form driven by JSON schema │ │ │ │ ├── LineItemTable.tsx # Dynamic line items (add/remove rows) │ │ │ │ └── TemplateSelector.tsx # PO/MOU + company picker │ │ │ ├── DocumentEditor/ │ │ │ │ ├── UploadZone.tsx # Drag-drop file upload │ │ │ │ ├── ExtractionReview.tsx # AI results + editable fields │ │ │ │ └── TransformSelector.tsx # Pick target company template │ │ │ └── shared/ │ │ │ ├── FieldInput.tsx # Reusable validated input │ │ │ ├── DocumentPreview.tsx # PDF iframe preview │ │ │ └── ProgressBar.tsx # AI processing indicator │ │ ├── pages/ │ │ │ ├── Creator.tsx │ │ │ ├── Editor.tsx │ │ │ └── History.tsx │ │ ├── api/ │ │ │ └── client.ts # Axios + React Query hooks │ │ ├── store/ │ │ │ └── docStore.ts # Zustand global state │ │ └── main.tsx │ └── package.json │ ├── backend/ # FastAPI (Python 3.11) │ ├── Dockerfile │ ├── requirements.txt │ ├── main.py # App entry, CORS, router registration │ ├── config.py # Settings via pydantic-settings │ ├── database.py # SQLAlchemy engine + session │ ├── models.py # ORM models: Document, Template, User │ ├── api/ │ │ ├── routes/ │ │ │ ├── generate.py # POST /api/generate │ │ │ ├── extract.py # POST /api/extract │ │ │ ├── transform.py # POST /api/transform │ │ │ ├── templates.py # GET /api/templates │ │ │ └── history.py # GET /api/history │ │ └── schemas.py # Pydantic request/response schemas │ ├── services/ │ │ ├── parser.py # pdfplumber + python-docx + OCR │ │ ├── extractor.py # Ollama LLM call + JSON parsing │ │ ├── generator.py # Jinja2 → WeasyPrint → PDF │ │ ├── docx_gen.py # docxtpl → DOCX output │ │ └── validator.py # Pydantic validation + confidence │ └── templates/ │ ├── schemas/ │ │ ├── po_schema.json │ │ └── mou_schema.json │ ├── html/ │ │ ├── base.html │ │ ├── po_company_abc.html │ │ ├── po_company_bp.html │ │ └── mou_standard.html │ ├── docx/ │ │ ├── po_company_abc.docx │ │ └── po_company_bp.docx │ └── css/ │ └── document.css │ └── data/ # Runtime volume (gitignored) ├── uploads/ ├── outputs/ ├── docgen.db └── logs/

Key Architectural Decisions

- JSON schemas drive both the frontend form render AND the LLM extraction prompt — single source of truth

- Jinja2 HTML templates → WeasyPrint is the PDF path; docxtpl is the DOCX path — both driven by the same field map

- Pydantic v2 models are shared between FastAPI route schemas and the LLM output validator

- SQLite stores document metadata and history; the actual files live in /data/outputs/

- Ollama runs as an independent Docker service — swappable for LM Studio or llama.cpp without changing the API client

4. 2-Week Phased Roadmap

Phase 1: Foundation (Days 1–3)

Set up the project skeleton, backend API, Ollama integration, and Docker Compose. At the end of Day 3, you should be able to start Ollama, send it a prompt via Python, and get back structured JSON.

- Day 1: Repo init, Docker Compose skeleton, FastAPI hello-world, Ollama service up

- Day 2: FastAPI routes scaffolded, Pydantic schemas, SQLite + SQLAlchemy setup

- Day 3: Ollama integration in Python, JSON extraction from a test prompt, basic file upload endpoint

Phase 2: Core Backend — Doc Generation (Days 4–6)

Build the template system and document generation pipeline. At the end of Day 6, you should be able to POST form data to /api/generate and receive a downloadable PDF.

- Day 4: JSON schema files (PO + MOU), Jinja2 HTML templates, WeasyPrint PDF generation

- Day 5: docxtpl DOCX generation, /api/generate endpoint wired up end to end, static CSS for PDF styling

- Day 6: Multi-company template support, template registry API, generation tested with sample data

Phase 3: Core Backend — Doc Parsing & AI Extraction (Days 7–9)

Build the Editor module backend. At the end of Day 9, uploading a real PO PDF should return extracted fields as validated JSON. This is the hardest phase.

- Day 7: pdfplumber parser, python-docx parser, OCR fallback with pytesseract

- Day 8: LLM extraction prompt, Ollama call in extractor.py, Pydantic post-validation, /api/extract route

- Day 9: /api/transform route (extract → populate different template), confidence scoring, error handling

Phase 4: React Frontend (Days 10–11)

Build both module UIs in React. Backend is complete — frontend work is primarily wiring up existing API endpoints with clean UI.

- Day 10: Project setup (Vite + TS + Tailwind), layout/routing, Creator form component driven by JSON schema

- Day 11: Editor module UI (upload zone, extraction review form, transform selector), History page, download links

Phase 5: Integration, Docker & Polish (Days 12–14)

Wire frontend to backend, full Docker Compose deployment, end-to-end testing, README documentation.

- Day 12: Full integration testing, CORS config, Docker builds for frontend + backend

- Day 13: Bug fixes, edge case handling (scanned PDFs, empty fields, large tables), loading states

- Day 14: Final Docker Compose with all 3 services, README, .env.example, deployment guide

5. Day-by-Day Task Board

Formatted for direct import into Jira or Microsoft Planner. Assignees: S = Sanjay, T = Teammate. Each task is 1–3 hours.

Week 1

| Day 1 – Mon — Setup & Infrastructure |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Initialise monorepo (git init, create frontend/ and backend/ dirs, .gitignore) | Sanjay | 1h | Critical |
| T-02 | Write docker-compose.yml with 3 services: nginx, fastapi, ollama (stub) | Teammate | 2h | Critical |
| T-03 | Create FastAPI main.py with /health endpoint and CORS middleware | Sanjay | 1h | Critical |
| T-04 | Pull Mistral 7B model via Ollama: ollama pull mistral:7b-instruct-q4_K_M | Teammate | 1h | High |
| T-05 | Set up Python venv, requirements.txt (fastapi, uvicorn, pydantic, httpx) | Sanjay | 1h | High |
| T-06 | Test Ollama endpoint manually via curl and confirm JSON mode works | Teammate | 1h | High |

Claude Usage: claude-sonnet-4-5 | ~10 chats | Ask Claude to generate docker-compose.yml and FastAPI boilerplate

| Day 2 – Tue — Backend Skeleton |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Define all Pydantic v2 schemas in api/schemas.py (POSchema, MOUSchema, ExtractedDoc) | Sanjay | 2h | Critical |
| T-02 | Set up SQLAlchemy + SQLite, create Document and Template ORM models in models.py | Teammate | 2h | Critical |
| T-03 | Scaffold all API route files: generate.py, extract.py, transform.py, templates.py, history.py | Sanjay | 2h | High |
| T-04 | Write config.py using pydantic-settings (reads from .env) | Teammate | 1h | High |
| T-05 | Test POST /api/generate stub returns 200 with mock data | Sanjay | 1h | Medium |

Claude Usage: claude-sonnet-4-5 | ~15 chats | Ask Claude for Pydantic schemas, SQLAlchemy models, FastAPI route stubs

| Day 3 – Wed — Ollama Integration |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Write services/extractor.py: async Ollama call, JSON mode, httpx client | Sanjay | 3h | Critical |
| T-02 | Write file upload endpoint (POST /api/upload) that saves to /data/uploads/ | Teammate | 2h | Critical |
| T-03 | Write services/parser.py: route PDF → pdfplumber, DOCX → python-docx | Teammate | 2h | High |
| T-04 | Integration test: upload a real PO PDF and verify raw text extraction works | Sanjay | 1h | High |
| T-05 | Commit all to git, push, verify Docker Compose starts all 3 services cleanly | Teammate | 1h | Medium |

Claude Usage: claude-sonnet-4-5 | ~18 chats | Ask Claude for the full extractor.py and parser.py with error handling

| Day 4 – Thu — Template System & PDF Generation |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Create po_schema.json and mou_schema.json in backend/templates/schemas/ | Sanjay | 2h | Critical |
| T-02 | Create base.html Jinja2 template with CSS variables and page layout for WeasyPrint | Teammate | 2h | Critical |
| T-03 | Create po_company_abc.html extending base.html with PO-specific blocks | Sanjay | 2h | High |
| T-04 | Write services/generator.py: Jinja2 → HTML → WeasyPrint → PDF bytes | Teammate | 2h | Critical |
| T-05 | Test: call generator.py with sample PO data, verify PDF opens and is readable | Sanjay | 1h | High |

Claude Usage: claude-sonnet-4-5 | ~18 chats | Ask Claude to write the full Jinja2 template HTML and generator.py service

| Day 5 – Fri — DOCX Output & /api/generate |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Install docxtpl, create po_company_abc.docx template with {{placeholders}} | Teammate | 2h | Critical |
| T-02 | Write services/docx_gen.py: docxtpl.render() with context dict | Sanjay | 2h | Critical |
| T-03 | Wire up POST /api/generate: validate input → choose PDF or DOCX path → return file | Sanjay | 2h | Critical |
| T-04 | Create GET /api/templates endpoint returning list of available schemas + company options | Teammate | 2h | High |
| T-05 | Manual end-to-end test: POST form data → download PDF → open in browser | Teammate | 1h | High |

Claude Usage: claude-sonnet-4-5 | ~16 chats | Ask Claude for docxtpl setup, /api/generate route logic, file response handling

| Day 6 – Sat — 2nd Company Template + API Polish |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Create po_company_bp.html (second company template, different branding/layout) | Sanjay | 3h | High |
| T-02 | Create mou_standard.html Jinja2 template for MOU document type | Teammate | 3h | High |
| T-03 | Add GET /api/history endpoint: return last 50 generated docs from SQLite | Sanjay | 2h | Medium |
| T-04 | Add error handling to generator.py: missing fields, WeasyPrint CSS errors | Teammate | 2h | High |

Claude Usage: claude-sonnet-4-5 | ~14 chats | Ask Claude to create the second template and the MOU template from scratch

Week 2

| Day 7 – Sun — Document Parsing Pipeline |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Extend parser.py: add pdfplumber table extraction (extract_tables()) | Sanjay | 2h | Critical |
| T-02 | Add pytesseract OCR fallback in parser.py for scanned/image PDFs | Teammate | 2h | High |
| T-03 | Write table formatter: convert raw pdfplumber table arrays to JSON rows | Sanjay | 2h | High |
| T-04 | Write services/validator.py: Pydantic ExtractedPO model + validation logic | Teammate | 2h | Critical |
| T-05 | Test parser on 3 different real PO PDFs (simple, table-heavy, scanned) | Sanjay | 2h | High |

Claude Usage: claude-sonnet-4-5 | ~18 chats | Ask Claude for the full pdfplumber table extraction and OCR fallback code

| Day 8 – Mon — AI Extraction & /api/extract |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Design and finalize the system prompt for PO field extraction (see Section 7 of this doc) | Sanjay | 2h | Critical |
| T-02 | Wire parser → extractor → validator pipeline in services/extractor.py | Teammate | 3h | Critical |
| T-03 | Implement POST /api/extract: upload file → parse → extract → return JSON + confidence | Sanjay | 2h | Critical |
| T-04 | Add confidence scoring: per-field 0–1 score based on null count and field completeness | Teammate | 2h | High |
| T-05 | Test extraction on 3 real PO samples, log accuracy, tune prompt | Sanjay | 2h | High |

Claude Usage: claude-sonnet-4-5 | ~20 chats | This is the hardest day — ask Claude to refine the extraction prompt iteratively

| Day 9 – Tue — Transform Pipeline & Polish |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Implement POST /api/transform: takes extracted JSON + target_template → calls generator | Sanjay | 3h | Critical |
| T-02 | Add MOU extraction schema (different fields from PO — parties, terms, duration, signatures) | Teammate | 2h | High |
| T-03 | Test full Editor module flow: upload ABC PO → extract → transform → download BP PO | Sanjay | 2h | Critical |
| T-04 | Add database write: save extracted + transformed doc metadata to SQLite | Teammate | 2h | Medium |
| T-05 | Add endpoint-level exception handlers and meaningful HTTP error messages | Sanjay | 2h | High |

Claude Usage: claude-sonnet-4-5 | ~16 chats | Ask Claude to write the /api/transform endpoint and MOU extraction schema

| Day 10 – Wed — React Frontend Setup + Creator Module |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Init Vite + React + TypeScript project, install Tailwind, React Query, Zustand, Axios | Teammate | 2h | Critical |
| T-02 | Create layout component (navbar, sidebar, main content area) | Teammate | 2h | High |
| T-03 | Write api/client.ts: typed Axios hooks for all 5 backend endpoints | Sanjay | 2h | Critical |
| T-04 | Build TemplateSelector component: fetches /api/templates, shows doc type + company picker | Sanjay | 2h | High |
| T-05 | Build CreatorForm component: renders fields dynamically from JSON schema, validates on submit | Sanjay | 3h | Critical |
| T-06 | Build LineItemTable component: add/remove rows, auto-calculates totals | Teammate | 2h | High |

Claude Usage: claude-sonnet-4-5 | ~18 chats | Ask Claude to generate React components. Provide the JSON schema so it can generate a dynamic form

| Day 11 – Thu — React Editor Module & History Page |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Build UploadZone component: drag-drop file upload, file type validation, upload progress | Teammate | 2h | Critical |
| T-02 | Build ExtractionReview component: shows extracted fields in editable form, highlights low-confidence fields in amber | Sanjay | 3h | Critical |
| T-03 | Build TransformSelector component: pick target company, trigger /api/transform | Sanjay | 2h | High |
| T-04 | Build DocumentPreview component: iframe PDF preview + download button | Teammate | 2h | High |
| T-05 | Build History page: table of past generated/transformed docs with download links | Teammate | 2h | Medium |
| T-06 | Wire Creator module end to end: form submit → /api/generate → preview + download | Sanjay | 2h | Critical |

Claude Usage: claude-sonnet-4-5 | ~18 chats | Ask Claude for each component individually. Provide the API response shape so it builds correct TypeScript types

| Day 12 – Fri — Full Integration & Docker |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Write frontend Dockerfile: multi-stage build (node build → nginx serve) | Teammate | 2h | Critical |
| T-02 | Write backend Dockerfile: python:3.11-slim, install deps, run uvicorn | Sanjay | 2h | Critical |
| T-03 | Finalize docker-compose.yml: volumes for /data, env vars, service dependencies, healthchecks | Sanjay | 2h | Critical |
| T-04 | Run full docker compose up and test both modules end to end inside containers | Teammate | 3h | Critical |
| T-05 | Fix CORS, nginx proxy config (/api/* → backend:8000), static file serving | Teammate | 2h | High |

Claude Usage: claude-sonnet-4-5 | ~14 chats | Ask Claude for Dockerfiles and nginx.conf — provide your docker-compose structure

| Day 13 – Sat — Bug Fixes & Edge Cases |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Test with 5+ real PO/MOU documents — log extraction failures and missing fields | Sanjay | 3h | Critical |
| T-02 | Fix top 3 extraction failures by refining the LLM system prompt | Sanjay | 2h | Critical |
| T-03 | Add loading spinners and progress bars for AI extraction (can take 30–60s on CPU) | Teammate | 2h | High |
| T-04 | Handle edge cases: empty PDFs, non-PO documents, very large line item tables | Teammate | 2h | High |
| T-05 | Add form validation error messages in frontend (missing required fields) | Sanjay | 1h | Medium |
| T-06 | Test on mobile viewport and fix any layout breaks | Teammate | 1h | Low |

Claude Usage: claude-sonnet-4-5 | ~14 chats | Ask Claude to help debug specific extraction failures — paste the raw extracted text

| Day 14 – Sun — Final Polish & Docs |
| --- |
| ID | Task | Assignee | Est. | Priority |
| T-01 | Write README.md: setup instructions, prerequisites, docker-compose up, first-use guide | Sanjay | 3h | Critical |
| T-02 | Create .env.example with all required environment variables and descriptions | Teammate | 1h | High |
| T-03 | Write DEPLOYMENT.md: intranet deployment guide, port configuration, backup strategy | Teammate | 2h | High |
| T-04 | Final round of testing: Creator module (PDF + DOCX), Editor module (PDF + DOCX in), History page | Sanjay | 2h | Critical |
| T-05 | Tag v0.1.0 release in git, write CHANGELOG.md | Sanjay | 1h | Medium |
| T-06 | Record a 5-minute screen recording demo of both modules | Teammate | 1h | Low |

Claude Usage: claude-sonnet-4-5 | ~8 chats | Ask Claude to help write README sections and review the docker-compose for production readiness

6. Claude Pro Usage Guide

You are using Claude Pro, which gives you access to the claude-sonnet-4-5 model (and claude-opus-4-6 for complex reasoning). Here is the optimal strategy for using Claude Pro to build this project efficiently within the 2-week window.

Model Selection

Use claude-sonnet-4-5 (default) for:

Writing all code: FastAPI routes, React components, Pydantic schemas, Jinja2 templates

Debugging runtime errors — paste the traceback and ask for a fix

Writing Docker configs, nginx.conf, requirements.txt

Iterating on the LLM extraction prompt (80% of your Claude usage)

Use claude-opus-4-6 only for:

Architecture decisions: when you're unsure which approach to take

Complex debugging that Sonnet can't crack after 2–3 attempts

Reviewing the extraction prompt for logical gaps

Claude Pro Usage by Phase

| Phase | Focus | Model | Usage/day | Effort |
| --- | --- | --- | --- | --- |
| Days 1–3 | Project setup, backend skeleton, Ollama integration | claude-sonnet-4-5 | ~15 chats/day | High |
| Days 4–6 | Template system, doc generation pipeline | claude-sonnet-4-5 | ~18 chats/day | High |
| Days 7–9 | AI extraction, parsing pipeline, Editor module | claude-sonnet-4-5 | ~20 chats/day | Very High |
| Days 10–11 | React frontend for both modules | claude-sonnet-4-5 | ~15 chats/day | High |
| Days 12–13 | Docker, integration testing, bug fixes | claude-sonnet-4-5 | ~12 chats/day | Medium |
| Day 14 | Polish, README, deployment docs | claude-sonnet-4-5 | ~8 chats/day | Medium |

Best Practices for Getting Code from Claude

- Always paste the full file context, not just the function — Claude writes better code when it sees what is already there

- Provide your Pydantic schema definitions when asking for route logic — Claude will match types exactly

- For the extraction prompt, paste a real document sample (redacted) so Claude can tune the prompt to real content

- When debugging, paste the full traceback + the relevant function — never just 'it's not working'

- Use follow-up prompts: 'add error handling', 'add type hints', 'make this async' rather than asking for everything at once

- Ask Claude to explain any code it generates that you do not understand — you own this code after the project

- At the end of each day, ask Claude to review what you built and suggest improvements — this catches architecture issues early

Conversation Management Tips

- Start a new Claude conversation for each major module (extractor.py, generator.py, React components)

- Keep a running file called claude_context.md with your schema definitions — paste it at the start of each session

- When a conversation gets long and Claude starts losing context, summarize what is built and start fresh

- Use Claude's Projects feature (if available on your plan) to maintain context across sessions

7. Master Prompt for Claude Code Execution

Copy this prompt at the start of each Claude session to give Claude full project context. Customize the [CURRENT TASK] section for each day's work.

Master Context Prompt

# DocGen — Project Context ## What we are building A fully local, self-hosted document creation and transformation app. No external API calls. Runs on an intranet. 2 modules: - Document Creator: form → template → PDF/DOCX - Document Editor: upload PO/MOU → AI extracts → regenerate in new format ## Stack - Frontend: React 18 + Vite + TypeScript + TailwindCSS + React Query + Zustand - Backend: FastAPI (Python 3.11) + SQLAlchemy + SQLite - AI: Ollama running Mistral 7B at http://localhost:11434 - Doc gen: Jinja2 + WeasyPrint (PDF) + docxtpl (DOCX) - Parsing: pdfplumber + python-docx + pytesseract - Deployment: Docker Compose (3 services: nginx, fastapi, ollama) ## Key Constraints - All Pydantic models use v2 syntax (model_config, not class Config) - All FastAPI routes are async - Ollama call uses format='json' mode for structured extraction - WeasyPrint CSS must use CSS2 table layouts (no flexbox/grid in PDF templates) - All files must include full type hints and docstrings ## Current file: [PASTE YOUR CURRENT FILE HERE] ## Current task: [DESCRIBE WHAT YOU WANT BUILT] Write production-quality code. Include error handling, logging, and inline comments for non-obvious logic. Return the complete file.

Prompt Templates by Task Type

For FastAPI Routes:

Here is my Pydantic schema for [X]. Write the FastAPI route POST /api/[route] that accepts this schema, calls services/[service].py, saves metadata to SQLite, and returns a FileResponse. Include HTTPException handling for file-not-found and validation errors.

For React Components:

Here is the API response shape from /api/extract: [paste JSON]. Write a React TypeScript component called ExtractionReview that renders all fields in an editable form. Fields with confidence < 0.7 should have an amber border. On submit, call the onConfirm(fields) prop.

For Debugging:

I have this Python traceback: [paste traceback]. Here is the relevant function: [paste function]. The function is supposed to [describe intent]. What is wrong and what is the fixed version?

For Prompt Tuning:

Here is my current extraction system prompt: [paste prompt]. Here is the raw text extracted from a PO: [paste text]. The model returned: [paste output]. The following fields were wrong or missing: [list]. Revise the system prompt to improve accuracy for these fields.

8. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| LLM extraction fails on complex tables | Editor module unusable for most real POs | Add user-editable extraction review form. Fall back to pytesseract + table-detect. Budget Day 13 for prompt tuning. |
| WeasyPrint CSS incompatibilities | PDFs render incorrectly | Restrict templates to CSS2 table-based layouts. Test each template on Day 4 before adding content. |
| Ollama slow on CPU-only machines | 30–90s extraction latency | Use Phi-3 Mini for CPU machines. Add async processing with a loading bar in the frontend. |
| Context window overflow on long POs | Extraction misses fields after page 2 | Chunk document by page. Extract header/footer fields in one call, line items in a second focused call. |
| Day 9 transform pipeline bugs block Day 10 | Frontend start delayed | Frontend dev can start React boilerplate and Creator form independently while transform is debugged. |
| Docker Compose networking issues | Services can't talk to each other | Use service names as hostnames (http://ollama:11434). Reserve Day 12 buffer for Docker debugging. |

DocGen — 2-Week Build Plan  |  Internal Use Only  |  Rev 1.0